## Φύλλο2
Test Case ID | Requirement Ref | Test Case Title | Priority | Test Technique | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Defect ID | Comments
TC-001 | REQ-1 | Quiz starts successfully | High | Use case testing | Python is installed and the quiz script (istqb_1-5.py) is in the current folder | 1. Open Terminal 2. Go to the folder containing the script 3. Run: python istqb_1-5.py | N/A | The application starts without errors, displays QA QUEST title and then Question 1 | The application starts without errors, diplays QA QUEST and Question 1 below | Pass
TC-002 | REQ-2 | Question and options are displayed correctly | High | Use case testing | The quiz has started | 1. Start the quiz 2. Observe question 1 3. Check the displayed options | N/A | Question 1 is displayed with its text and four options | Question 1 is displayed with its text and options A-D | Pass
TC-003 | REQ-4 | Corrext answer is recognised | High | Equivalence partitioning | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1 , type test data and press Enter 3. Read the feedback message | Input: C | The application displays "Correct! +1point" | The application displays "Correct! +1point" | Pass
TC-004 | REQ-5 | Incorrect answer is recognised | High | Equivalence partitioning | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, type test data and press Enter 3. Read the feedback message | Input: A | The application displays "Not quite. Correct Answer: C" | The application displays "Not quite. Correct Answer: C" | Pass
TC-005 | REQ-3 | Lower case answer is accepted | Medium | Equivalence partitioning | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, type test data and press Enter 3. Read the feedback message | Input: c | The application displays "Correct! +1point" | The application displays "Correct! +1point" | Pass
TC-006 | REQ-3 | Answer with surrounding spaces is accepted | Medium | Equivalence partitioning | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, type test data and press Enter 3. Read the feedback message | Input: two spaces, then C, then two spaces | The application displays "Correct! +1point" | The application displays "Correct! +1point" | Pass
TC-007 | REQ-3 | Lower case answer with surrounding spaces is accepted | Low | Equivalence partitioning (combined inputs) | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, type test data and press Enter 3. Read the feedback message | Input: one space, then c, then one space | The application displays "Correct! +1point" | The application displays "Correct! +1point" | Pass
TC-008 | REQ-5 | Letter outside A-D is treated as incorrect | Medium | Equivalence partitioning | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, type test data and press Enter 3. Read the feedback message | Input: E | The application displays "Not quite. Correct Answer: C" | The application displays "Not quite. Correct Answer: C" | Pass
TC-009 | REQ-5 | Blank answer is treated as incorrect | Medium | Boundary value analysis (input length ) | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, leave answer empty and press Enter 3. Read the feedback message | Input: empty (Enter only) | The application displays "Not quite. Correct Answer: C" | The application displays "Not quite. Correct Answer: C" | Pass
TC-010 | REQ-5 | Number is treated as incorrecy | Medium | Equivalence partitioning | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, type test data and press Enter 3. Read the feedback message | Input: 5 | The application displays "Not quite. Correct Answer: C" | The application displays "Not quite. Correct Answer: C" | Pass
TC-011 | REQ-5 | Two characters are treated as incorrect | Low | Boundary value analysis (input length 2) | The quiz is running and Question 1 is displayed. The correct answer is known | 1. Start the quiz 2. At Question 1, type test data and press Enter 3. Read the feedback message | Input: AB | The application displays "Not quite. Correct Answer: C" | The application displays "Not quite. Correct Answer: C" | Pass
TC-012 | REQ-6 | Quiz finishes after the last question and the score stays visible | High | Use case testing | The quiz script is ready to run and Question 1 is displayed. Correct answers to all questions are known | 1. Start the quiz 2. For each of the five questions, type the answer from the Test Data 3. Read the final score | Q1:A, Q2: A, Q3: A, Q4: A, Q5:A | All five questions are shown in order. After the fifth answer the application displays "Game over! Yout score is 2/5" and the text stays visible in the terminal | Question 5 is not displayed correctly. After submitting the fifth answer, the terminal closes immediately, preventing verification of the final score. | Fail | Question 5 SCRUM-7 Terminal closes: SCRUM-6
TC-013 | REQ-6 | Final score when all answers are corret | High | Boundary value analysis (maximum score) | The quiz script is ready to run and Question 1 is displayed. Correct answers to all questions are known | 1. Start the quiz 2. For each of the five questions, type the answer from the Test Data 3. Read the final score | Q1: C, Q2: A, Q3: A, Q4: B, Q5: B | The application displays "Correct! +1point" after every answer and "Game over! Your score: 5/5" | The quiz completed, but the terminal closed immediately after the fifth answer, preventing verification of the final score. | Blocked
TC-014 | REQ-6 | Final score when all answers are incorret | Medium | Boundary value analysis (minimum score) | The quiz script is ready to run and Question 1 is displayed. Correct answers to all questions are known | 1. Start the quiz 2. For each of the five questions, type the answer from the Test Data 3. Read the final score | Q1: A, Q2: B, Q3: B, Q4: A, Q5: A | The application displays "Not quite. Correct Answer: [letter]" after every answer and "Game over! Your score: 0/5" | The quiz completed, but the terminal closed immediately after the fifth answer, preventing verification of the final score. | Blocked
TC-015 | REQ-6 | Final score when one answer is correct | Medium | Boundary value analysis (minimum +1) | The quiz script is ready to run and Question 1 is displayed. Correct answers to all questions are known | 1. Start the quiz 2. For each of the five questions, type the answer from the Test Data 3. Read the final score | Q1: C, Q2: B, Q3: B, Q4: A, Q5:A | The application displays "Game over! Your score: 1/5" | The quiz completed, but the terminal closed immediately after the fifth answer, preventing verification of the final score. | Blocked
TC-016 | REQ-6 | Final score when three answers are correct | Medium | Equivalence partitioning (middle score) | The quiz script is ready to run and Question 1 is displayed. Correct answers to all questions are known | 1. Start the quiz 2. For each of the five questions, type the answer from tge Test Data 3. Read the final score | Q1: C, Q2: A, Q3:A, Q4:A, Q5:A | The application displays "Game over! Your score: 3/5" | The quiz completed, but the terminal closed immediately after the fifth answer, preventing verification of the final score. | Blocked
TC-017 | REQ-6 | Final score when four answers are correct | Low | Boundary value analysis (maximum-1) | The quiz script is ready to run and Question 1 is displayed. Correct answers to all questions are known | 1. Start the quiz 2. For each of the five questions, type the answer from tge Test Data 3. Read the final score | Q1: C, Q2: A, Q3:A. Q4: B, Q5:A | The application displays "Game over! Your score: 4/5" | The quiz completed, but the terminal closed immediately after the fifth answer, preventing verification of the final score. | Blocked
Project | Python Testing Quiz
Application Version | 1.0
Test Environment | Local Computer
Operationg System | Windows 10
Python Version | Python 3.14 (64-bit)
Execution Date | 2026-10-18